## Sheet1
User Story | Estimated Complexity | Done? | Tasks | Pair Assigned | Estimated Effort
1. Users can login to their dashboards (main page) using their Staff ID | 2 | N | Create Form | Daniel, Aaron
Add ASP Functionality
Add CSS
2. Research Staff can create a new project | 8 | N | Give Name | Marc, Scott
Give Details
Upload Excel File
3. Research Staff can view all self-created projects | 2 | N | Database Select Statement | Marc, Scott
Create and insert info into Form
Add CSS
4. RIS Staff can view all created projects | 2 | N | Select * from Table | Daniel, Aaron
5. RIS Staff can access a project (view its details) | 4 | N | Select * using selected Product ID | Daniel, Aaron
Bring into Form/Other view
Add CSS
Add Options for other functions
6. RIS Staff can access(Download) an Excel file from a selected project | 6 | N | Select the option to download | Daniel, Aaron
Perform download function
Give option to re-upload
7. RIS Staff can upload an edited excel file | 4 | N | Give Path to File | Marc, Scott
File Upload
Add Comment to history table
Update History table
8. RIS Staff can request researcher for signature | 5 | N | Send Email | Connor, Ryan
Update Project Status - "Include further action from researcher"
9. Researcher sends project to Assoc. Dean for signature | 5 | N | Send Email | Connor, Ryan
Update Project "Awaiting signature from Associate Dean
10. Associate Dean can sign once complete | 6 | N | Give Electronic Signature - "Signed by STAFFID" | Connor, Ryan
Send to Dean
Update Project Status - "Awaiting Dean Signature"
11. Dean can sign once complete | 6 | N | Give Electronic Signature - "Signed by STAFFID" | Connor, Ryan
Set Project Status - "Approved"
|  |  | Not Started | In Progress | Complete