## Sheet1
User Story | Estimated Complexity | Done? | Tasks | Owner | Estimated Effort | Monday | Tuesday | Wednesday | Thursday | Friday
1. Users can login to their dashboards (main page) using their Staff ID | 2 | Y | Create log in form in ASP.NET | Daniel | 2 | 1 | 1
|  |  | Add additional required log in functionality with DB | Aaron | 3 | 2 | 1
|  |  | Add CSS | Aaron | 1 |  | 1
2. Research Staff can create a new project | 6 | Y | Give project name | Marc | 1 | 2
|  |  | Give description of project | Marc | 1 | 1
|  |  | Upload excel file | Scott | 3 | 2 | 2
3. Research Staff can view all self-created projects | 2 | Y | Pull relevant data from DB | Scott | 2 |  |  | 2
|  |  | Create and insert info into table | Scott | 1 |  |  | 1
|  |  | Add CSS | Marc | 1 |  | 2
4. RIS Staff can view all created projects | 2 | Y | Select * from Table (using built in view generator) | Daniel | 2 |  | 2
5. RIS Staff can access a project (view its details) | 4 | Y | Retrieve data from database | Aaron | 1 |  | 1
|  |  | Bring into Form/Other view (pass through session variable) | Aaron | 2 |  |  | 2
|  |  | Add CSS | Daniel | 1 |  |  | 1
|  |  | Add Options for other functions | Daniel | 1 |  |  | 1
6. RIS Staff can access(Download) an Excel file from a selected project | 6 | Y | Select the option to download | Daniel | 1 |  |  |  | 1
|  |  | Perform download function | Arron | 2 |  |  |  | 3
|  |  | Give option to re-upload | Daniel | 1 |  |  |  | 1
7. RIS Staff can upload an edited excel file | 4 | Y | User selects file from file browser | Marc | 1 |  |  | 1
|  |  | File Upload function | Scott | 2 |  |  |  | 2
|  |  | Add Comment to history table | Scott | 1 |  |  |  | 2
|  |  | Update History table | Marc | 1 |  |  | 1
8. RIS Staff can request researcher for signature | 5 | N | Send Email to Signature | Connor | 2 | 1
|  |  | Update Project Status - "Include further action from researcher" | Connor | 1 | 1
9. Researcher sends project to Assoc. Dean for signature | 5 | N | Send Email- | Connor | 2 |  | 2
|  |  | Update Project "Awaiting signature from Associate Dean | Ryan | 1 | 2 | 1
10. Associate Dean can sign once complete | 6 | N | Give Electronic Signature - "Signed by STAFFID" | Connor | 2 |  |  | 2
|  |  | Send to Dean | Ryan | 2 |  | 1 | 1
|  |  | Update Project Status - "Awaiting Dean Signature" | Ryan | 1 |  |  | 1
11. Dean can sign once complete | 6 | N | Give Electronic Signature - "Signed by STAFFID" | Connor | 2 |  |  |  | 2
|  |  | Set Project Status - "Approved" | Ryan | 2 |  |  |  | 2 | 1
|  |  | Not Started | In Progress | Complete
Estimated Velocity | 48
Actual Velocity
Person Hours per 1 Complexity
Marc | 3
Scott | 2
Daniel | 2
Connor | 3
Ryan | 4