## Sheet1
User Story | Estimated Complexity | Done? | Tasks | Owner | Estimated Effort | Monday | Tuesday | Wednesday | Thursday | Friday
1. Research staff can edit details of a project currently in progress |  |  | Create form | Pair 1 - M & S
Add functionality to retreive existing information from DB
Add functionality to update DB with new information
Add CSS
2. Research staff can check progression currently in progress |  |  | Retreive all comments from DB | Pair 2 - D & A
Display in list
3. Researcher can sign the excel file electronically to send to dean |  |  | Fix current issues | Pair 3 - R & C
4. RIS Staff can check the progress status of each project in the system |  |  | Add Functionality on create project | Pair 2 - D & A
Add load in from db
Add CSS
5. RIS staff can request the researcher for further information |  |  | Create Form | Pair 3 - R & C
Add Request to DB
Add change to changes in DB
6. RIS staff can request the researcher for clarification |  |  | Use Further Info Form | Pair 3 - R & C
Add Request to DB
Add change to changes in DB
7. RIS staff can request the researcher for corrections |  |  | Use Further Info Form | Pair 3 - R & C
Add Request to DB
Add change to changes in DB
8. Sign out Functioanlity |  |  | Add Sign option | Pair 2 - D & A
Add sign out functionality
9. History Changes on creation |  |  | Create Functionality of adding history to project | Pair 1 - M & S
Save to DB